## Coverpage - Page 1
Project Plan October 5, 2022 Issued by: Algorithmic Alchemist Team Lead Sierra Harris Team Members Bryant Lam Abhay Solanki Faisal Al Muharrami Kevin Thai David Chan Github: https://github.com/abhay772/AA_Senior_Project/

## Table of Contents - Page 2
Table of Contents
Cover Page ........................................... | 1
Table of Contents .................................. | 2
Version History ...................................... | 3
Detailed Project Plan ............................. | 4
Glossary ................................................ | 5
References ............................................ | 6

## Version History - Page 3
Version History
Version Number | Date | Reason for Change
v1.0.0.0 | 2022-10-05

## Detailed Project Plan - Page 4
PMtoGo |  | Team Lead: Sierra Harris
Team Members
Team Algorithmic Alchemist |  | Abhay Solanki Bryant Lam David Chan Faisal Al Murharrami Kevin Thai
[5 empty] | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01
Work Items |  | Start | End | Total Hours | Week 9/4/22 | Week 9/11/22 | Week 9/18/22 | Week 9/25/22 | Week 10/2/22 | Week 10/9/22 | Week 10/16/22 | Week 10/23/22 | Week 10/30/22 | Week 11/6/22 | Week 11/13/22 | Week 11/20/22 | Week 11/27/22 | Week 12/4/22 | Week 12/11/22 | Week 12/18/22 | Week 12/25/22
1 | Request For Proposal | 2022-08-01 | 2022-09-01 | 32
Milestone 1 |  | 2022-09-01 | 2022-10-01 | 98
2 | Business Rules Document | 9th of Sept | 5th of Oct | 64
3 | High-Level Design | 9th of Sept | 5th of Oct | 16
4 | Project Plan | 9th of Sept | 5th of Oct | 16
5 | Team Review 1 | 5th of Oct | 5th of Oct | 2
Milestone 2 |  | 2022-10-01 | 2022-11-01 | 194
6 | Network Diagram | 6th of Oct | 9th of Nov | 32
7 | Low-Level Design | 6th of Oct | 9th of Nov | 64
8 | Registration | 6th of Oct | 9th of Nov | 32
9 | Logging | 6th of Oct | 9th of Nov | 64
10 | Team Review 2 | 9th of Nov | 9th of Nov | 2
Milestone 3 |  | 2022-11-01 | 2022-12-01 | 178
11 | Authentication/ User Management | 9th of Nov | 14th of Dec | 64 | [11 empty] | Thanksgiving Break
12 | Authorization/ User Management | 9th of Nov | 14th of Dec | 64
13 | Account Recovery/ User Management | 9th of Nov | 14th of Dec | 32
14 | Bill Of Materials | 9th of Nov | 14th of Dec | 16
| Team Review 3 | 14th of Dec | 14th of Dec | 2
[5 empty] | 2023-01-01 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-02 |  |  |  | 2023-04-02 |  |  |  |  | 2023-05-03
Work Items |  | Start | End | Total Hours | Week 1/1/23 | Week 1/8/23 | Week 1/15/23 | Week 1/22/23 | Week 1/29/23 | Week 2/5/23 | Week 2/12/23 | Week 2/19/23 | Week 2/26/23 | Week 3/5/23 | Week 3/12/23 | Week 3/19/23 | Week 3/26/23 | Week 4/2/23 | Week 4/9/23 | Week 4/16/23 | Week 4/23/23 | Week 4/30/23 | Week 5/7/23 | Week 5/14/23
Milestone 4: User Update |  | 2023-01-01 | 2023-01-01
15 | User Profile | 2023-01-01 | 2023-01-01 | 80
| View History | 19th of Jan | 25th of Jan | 32
| View Rating | 22nd of Jan | 25th of Jan | 32
| User Profile Testing | 25th of Jan | 30th of Jan | 16
16 | Dashboard | 2023-01-01 | 2023-01-01 | 84
| View Rating | 19th of Jan | 30th of Jan | 16
| View Upcoming Appointment | 19th of Jan | 30th of Jan | 16
| View Property Value | 19th of Jan | 30th of Jan | 36
| Dashboard Testing | 25th of Jan | 30th of Jan | 16
Milestone 5: Planning Update |  | 2023-01-01 | 2023-02-01
17 | DIY Manager | 2023-02-01 | 2023-02-28 | 80
| DIY Manager | 1st of Feb | 15th of Feb | 32
| Upload DIY | 5th of Feb | 15th of Feb | 16
| Save DIY | 5th of Feb | 15th of Feb | 16
| DIY Manager Testing | 15th of Feb | 20th of Feb | 16
18 | Calendar | 2023-01-29 | 2023-02-05 | 80
| Schedule Appointment | 29th of Jan | 6th of Feb | 32
| Modify / Delete Appointment | 29th of Jan | 6th of Feb | 16
| View Appointments | 6th of Feb | 13th of Feb | 16
| Calendar Testing | 6th of Feb | 13th of Feb | 16
Milestone 6: Management Update |  | 2023-02-01 | 2023-03-01
19 | User Management | 6th of Feb | 20th of Feb | 64
20 | Service Management | 2023-02-19 | 2023-03-01 | 128
| Service Request | 20th of Feb | 1st of March | 48
| Frequency Change/Cancellation | 1st of March | 8th of March | 32
| Service Rating | 1st of March | 8th of March | 20
| Service Mangement Testing | 9th of March | 15th of March | 28
21 | Request Management | 2023-03-01 | 2023-03-01 | 96
| View Request | 15th of March | 22th of March | 32
| Update Service | 22th of March | 29th of March | 32
| Service Rating | 22th of March | 29th of March | 16
| Request Management Testing | 22th of March | 29th of March | 16
Milestone 6: Property Update |  | 2023-03-01 | 2023-04-01
22 | Property Evaluation | 2023-03-01 | 2023-04-01 | 48
| Evaluate Property | 29th of March | 5th of April | 32
| Property Evaluation Testing | 29th of March | 5th of April | 16
| Maintenance and Renovation | 2023-03-01 | 2023-04-01 | 80
| Compare | 29th of March | 5th of April | 16
| Estimate | 5th of April | 12th of April | 16
| Smart Saver | 5th of April | 12th of April | 32
| Testing | 10th of April | 12th of April | 16
Milestone 6: Property Update |  | 2023-04-01 | 2023-05-01
23 | Neighborhood Crime Alerts | 2023-04-01 | 2023-05-01 | 112
| Add Crime Alert | 12th of April | 24th of April | 64
| Edit/Delete Crime Alert | 24th of April | 26th of April | 16
| Neighborhood Crime Alerts Testing | 24th of April | 1st of May | 32
24 | Document Storage | 2023-04-01 | 2023-05-01 | 80
| Optical Text Search | 24th of April | 1st of May | 32
| Upload Document | 1st of May | 8th of May | 16
| Sign Document | 1st of May | 8th of May | 16
| Document Storage Testing | 8th of May | 10th of May | 16
25 | Final Testing and Bugfixes | 10th of May | 19th of May

## Glossary - Page 5
Term/Acronym | Definition
High-Level Design | The architecture diagram provides an overview of an entire system, identifying the main components that would be developed for the product and their interfaces.
Low-Level Design | It is a component-level design process that follows a step-by-step refinement process.
Bill of Materials | It is a list of the raw materials, sub-assemblies, intermediate assemblies, sub-components, parts, and the quantities of each needed to manufacture an end product.
DIY | It is an acronym for “Do it yourself” and is the method of building, modifying, or repairing things by oneself without the direct aid of professionals or certified experts. Academic research has described DIY as behaviors where "individuals use raw and semi-raw materials and parts to produce, transform, or reconstruct material possessions