## A.A. Sprint 7
Date
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Ideal hours per day and hours left
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Remaining Work | Time of Tasks: | 40 | Algorithmic Alchemist |  |  |  | Remaining Work | Time of Tasks: | 135
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 40 | Ideal hrs/day: | 5.7143 | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 135 | Ideal hrs/day: | 19.2857
0 | 2022-11-15 | 8 | 6 | 34 | 40 |  | 0 | 2022-11-15 | 19 | 21 | 114 | 115.7143
1 | 2022-11-16 | 6 | 5 | 29 | 34.2857 |  | 1 | 2022-11-16 | 24 | 16 | 98 | 96.4286
2 | 2022-11-17 | 7 | 6 | 23 | 28.5714 |  | 2 | 2022-11-17 | 35 | 27.5 | 70.5 | 77.1429
3 | 2022-11-18 | 6 | 5 | 18 | 22.8571 |  | 3 | 2022-11-18 | 27 | 20.5 | 50 | 57.8571
4 | 2022-11-19 | 3 | 1.5 | 16.5 | 17.1429 |  | 4 | 2022-11-19 | 20 | 11.5 | 38.5 | 38.5714
5 | 2022-11-20 | 3 | 1.5 | 15 | 11.4286 |  | 5 | 2022-11-20 | 18 | 11.5 | 27 | 19.2857
6 | 2022-11-21 | 6 | 4 | 11 | 5.7143 |  | 6 | 2022-11-21 | 14 | 10 | 17 | 0
David Chan |  |  |  | Remaining Work | Time of Tasks: | 24
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 24 | Ideal hrs/day: | 3.4286
0 | 2022-11-15 | 3 | 4 | 20 | 24
1 | 2022-11-16 | 5 | 2 | 18 | 20.5714
2 | 2022-11-17 | 3 | 1.5 | 16.5 | 17.1429
3 | 2022-11-18 | 3 | 1.5 | 15 | 13.7143
4 | 2022-11-19 | 7 | 3 | 12 | 10.2857
5 | 2022-11-20 | 5 | 3 | 9 | 6.8571
6 | 2022-11-21 | 2 | 2 | 7 | 3.4286
Bryant Lam |  |  |  | Remaining Work | Time of Tasks: | 21
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 21 | Ideal hrs/day: | 3
0 | 2022-11-15 | 4 | 3 | 18 | 21
1 | 2022-11-16 | 5 | 4 | 14 | 18
2 | 2022-11-17 | 8 | 6 | 8 | 15
3 | 2022-11-18 | 8 | 6 | 2 | 12
4 | 2022-11-19 | 3 | 2 | 0 | 9
5 | 2022-11-20 | 3 | 2 | -2 | 6
6 | 2022-11-21 | 3 | 2 | -4 | 3
Abhay Solanki |  |  |  | Remaining Work | Time of Tasks: | 18
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 18 | Ideal hrs/day: | 4.5
0 | 2022-11-15 | 6 | 5 | 13 | 18
1 | 2022-11-16 | 3 | 2 | 11 | 13.5
2 | 2022-11-17 | 8 | 6 | 5 | 9
3 | 2022-11-18 | 5 | 3 | 2 | 4.5
Faisal AlMuharrami |  |  |  | Remaining Work | Time of Tasks: | 20
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 20 | Ideal hrs/day: | 2.8571
0 | 2022-11-15 | 4 | 4 | 16 | 20
1 | 2022-11-16 | 5 | 3 | 13 | 17.1429
2 | 2022-11-17 | 5 | 4 | 9 | 14.2857
3 | 2022-11-18 | 3 | 3 | 6 | 11.4286
4 | 2022-11-19 | 4 | 4 | 2 | 8.5714
5 | 2022-11-20 | 4 | 3 | -1 | 5.7143
6 | 2022-11-21 | 1 | 1 | -2 | 2.8571
Tania Adame |  |  |  | Remaining Work | Time of Tasks: | 12
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 12 | Ideal hrs/day: | 2.4
0 | 2022-11-17 | 4 | 4 | 8 | 12
1 | 2022-11-18 | 2 | 2 | 6 | 9.6
2 | 2022-11-19 | 3 | 1 | 5 | 7.2
3 | 2022-11-20 | 3 | 2 | 3 | 4.8
4 | 2022-11-21 | 2 | 1 | 2 | 2.4

## A.A. Sprint 8
Date
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Ideal hours per day and hours left
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Remaining Work | Time of Tasks: | 12 | Algorithmic Alchemist |  |  |  | Remaining Work | Time of Tasks: | 65
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 12 | Ideal hrs/day: | 4 | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 65 | Ideal hrs/day: | 10.8333
0 | 2022-11-22 | 6 | 5 | 7 | 12 |  | 0 | 2022-11-22 | 26 | 18 | 47 | 54.1667
1 | 2022-11-23 | 6 | 4 | 3 | 8 |  | 1 | 2022-11-23 | 21 | 14 | 33 | 43.3333
2 | 2022-11-28 | 3(sick) | 2 | 1 | 4 |  | 2 | 2022-11-24 | 2 | 1 | 32 | 32.5
[7 empty] | 3 | 2022-11-26 | 5 | 5 | 27 | 21.6667
[7 empty] | 4 | 2022-11-27 | 10 | 8 | 19 | 10.8333
[7 empty] | 5 | 2022-11-28 | 15 | 11 | 8 | 0
David Chan |  |  |  | Remaining Work | Time of Tasks: | 10
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 10 | Ideal hrs/day: | 3.3333
0 | 2022-11-22 | 4 | 3 | 7 | 10
1 | 2022-11-23 | 6 | 3 | 4 | 6.6667
2 | 2022-11-28 | 0 | 2 | 2 | 3.3333
Bryant Lam |  |  |  | Remaining Work | Time of Tasks: | 8
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 8 | Ideal hrs/day: | 2.6667
0 | 2022-11-22 | 4 | 3 | 5 | 8
1 | 2022-11-27 | 4 | 3 | 2 | 5.3333
2 | 2022-11-28 | 4 | 4 | -2 | 2.6667
Abhay Solanki |  |  |  | Remaining Work | Time of Tasks: | 18
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 18 | Ideal hrs/day: | 3.6
0 | 2022-11-22 | 5 | 4 | 14 | 18
1 | 2022-11-23 | 4 | 3 | 11 | 14.4
2 | 2022-11-26 | 5 | 4 | 7 | 10.8
3 | 2022-11-27 | 4 | 3 | 4 | 7.2
4 | 2022-11-28 | 6 | 4 | 0 | 3.6
Faisal AlMuharrami |  |  |  | Remaining Work | Time of Tasks: | 8
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 8 | Ideal hrs/day: | 2.6667
0 | 2022-11-22 | 4 | 3 | 5 | 8
1 | 2022-11-23 | 4 | 3 | 2 | 5.3333
2 | 2022-11-24 | 2 | 1 | 1 | 2.6667
Tania Adame |  |  |  | Remaining Work | Time of Tasks: | 9
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 9 | Ideal hrs/day: | 1.2857
0 | 2022-11-22 | 3 | 2 | 7 | 9
1 | 2022-11-23 | 1 | 1 | 6 | 7.7143
2 | 2022-11-24 | 0 | 0 | 6 | 6.4286
3 | 2022-11-25 | 0 | 0 | 6 | 5.1429
4 | 2022-11-26 | 0 | 0 | 6 | 3.8571
5 | 2022-11-27 | 2 | 2 | 4 | 2.5714
6 | 2022-11-28 | 2 | 1 | 3 | 1.2857

## A.A. Sprint 9
Date
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Ideal hours per day and hours left
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Remaining Work | Time of Tasks: | 35 | Algorithmic Alchemist |  |  |  | Remaining Work | Time of Tasks: | 120
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 35 | Ideal hrs/day: | 7 | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 120 | Ideal hrs/day: | 13.3333
0 | 2022-11-29 | 7 | 6 | 29 | 35 |  | 0 | 2022-11-29 | 15 | 12 | 108 | 106.6667
1 | 2022-11-30 | 5 | 4 | 25 | 28 |  | 1 | 2022-11-30 | 25 | 20 | 88 | 93.3333
2 | 2022-12-02 | 4 | 3 | 22 | 21 |  | 2 | 2022-12-01 | 8 | 7 | 81 | 80
3 | 2022-12-06 | 5 | 3 | 19 | 14 |  | 3 | 2022-12-02 | 9 | 7 | 74 | 66.6667
4 | 2022-12-07 | 6 | 5 | 14 | 7 |  | 4 | 2022-12-03 | 7 | 6 | 68 | 53.3333
[7 empty] | 5 | 2022-12-04 | 12 | 12 | 56 | 40
[7 empty] | 6 | 2022-12-05 | 10 | 8 | 48 | 26.6667
[7 empty] | 7 | 2022-12-06 | 19 | 14 | 34 | 13.3333
[7 empty] | 8 | 2022-12-07 | 30 | 26 | 8 | 0
David Chan |  |  |  | Remaining Work | Time of Tasks: | 18
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 18 | Ideal hrs/day: | 3
0 | 2022-11-29 | 4 | 3 | 15 | 18
1 | 2022-11-30 | 5 | 4 | 11 | 15
2 | 2022-12-04 | 1 | 1 | 10 | 12
3 | 2022-12-05 | 5 | 2 | 8 | 9
4 | 2022-12-06 | 5 | 5 | 3 | 6
5 | 2022-12-07 | 5 | 5 | -2 | 3
Bryant Lam |  |  |  | Remaining Work | Time of Tasks: | 12
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 12 | Ideal hrs/day: | 2.4
0 | 2022-11-29 | 3 | 2 | 10 | 12
1 | 2022-11-30 | 4 | 3 | 7 | 9.6
2 | 2022-12-03 | 3 | 3 | 4 | 7.2
3 | 2022-12-04 | 2 | 1 | 3 | 4.8
4 | 2022-12-07 | 6 | 5 | -2 | 2.4
Abhay Solanki |  |  |  | Remaining Work | Time of Tasks: | 25
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 25 | Ideal hrs/day: | 3.5714
0 | 2022-11-29 | 4 | 3 | 22 | 25
1 | 2022-11-30 | 6 | 5 | 17 | 21.4286
2 | 2022-12-01 | 5 | 4 | 13 | 17.8571
3 | 2022-12-04 | 5 | 5 | 8 | 14.2857
4 | 2022-12-05 | 4 | 2 | 6 | 10.7143
5 | 2022-12-06 | 4 | 3 | 3 | 7.1429
6 | 2022-12-07 | 6 | 5 | -2 | 3.5714
Faisal AlMuharrami |  |  |  | Remaining Work | Time of Tasks: | 20
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 20 | Ideal hrs/day: | 2.2222
0 | 2022-11-29 | 1 | 1 | 19 | 17.7778
1 | 2022-11-30 | 3 | 2 | 17 | 15.5556
2 | 2022-12-01 | 2 | 1 | 16 | 13.3333
3 | 2022-12-02 | 2 | 2 | 14 | 11.1111
4 | 2022-12-03 | 2 | 2 | 12 | 8.8889
5 | 2022-12-04 | 2 | 2 | 10 | 6.6667
6 | 2022-12-05 | 4 | 3 | 7 | 4.4444
7 | 2022-12-06 | 2 | 2 | 5 | 2.2222
8 | 2022-12-07 | 6 | 6 | -1 | 0
Tania Adame |  |  |  | Remaining Work | Time of Tasks: | 10
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 10 | Ideal hrs/day: | 1.1111
0 | 2022-11-29 | 0 | 0 | 10 | 10
1 | 2022-11-30 | 2 | 2 | 8 | 8.8889
2 | 2022-12-01 | 1 | 2 | 6 | 7.7778
3 | 2022-12-02 | 3 | 2 | 4 | 6.6667
4 | 2022-12-03 | 2 | 1 | 3 | 5.5556
5 | 2022-12-04 | 2 | 3 | 0 | 4.4444
6 | 2022-12-05 | 1 | 2 | -2 | 3.3333
7 | 2022-12-06 | 3 | 1 | -3 | 2.2222
8 | 2022-12-07 | 1 | 0 | -3 | 1.1111

## A.A. Sprint 10
Date
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Ideal hours per day and hours left
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Remaining Work | Time of Tasks: | 10 | Algorithmic Alchemist |  |  |  | Remaining Work | Time of Tasks: | 95
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 10 | Ideal hrs/day: | 1.6667 | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 95 | Ideal hrs/day: | 15.8333
0 | 2022-12-09 | 4 | 2.5 | 7.5 | 10 |  | 0 | 2022-12-08 | 5 | 5 | 90 | 95
1 | 2022-12-10 | 7 | 6 | 1.5 | 8.3333 |  | 1 | 2022-12-09 | 13 | 10.5 | 79.5 | 79.1667
2 | 2022-12-11 | 6 | 6 | -4.5 | 6.6667 |  | 2 | 2022-12-10 | 21 | 18 | 61.5 | 63.3333
3 | 2022-12-12 | 10am-1 |  | -4.5 | 5 |  | 3 | 2022-12-11 | 19 | 18 | 43.5 | 47.5
4 | 2022-12-13 |  |  | -4.5 | 3.3333 |  | 4 | 2022-12-12 | 17 | 12 | 31.5 | 31.6667
5 | 2022-12-14 |  |  | -4.5 | 1.6667 |  | 5 | 2022-12-13 | 0 | 0 | 31.5 | 15.8333
[7 empty] | 6 | 2022-12-14 | 0 | 0 | 31.5 | 0
David Chan |  |  |  | Remaining Work | Time of Tasks: | 25
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 25 | Ideal hrs/day: | 4.1667
0 | 2022-12-09 | 3 | 2 | 23 | 25
1 | 2022-12-10 | 8 | 6 | 17 | 20.8333
2 | 2022-12-11 | 8 | 6 | 11 | 16.6667
3 | 2022-12-12 | 8 | 5 | 6 | 12.5
4 | 2022-12-13 |  |  | 6 | 8.3333
5 | 2022-12-14 |  |  | 6 | 4.1667
Bryant Lam |  |  |  | Remaining Work | Time of Tasks: | 8
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 8 | Ideal hrs/day: | 2.6667
0 | 2022-12-12 | 5 | 4 | 4 | 5.3333
1 | 2022-12-13 |  |  | 4 | 2.6667
2 | 2022-12-14 |  |  | 4 | 0
Abhay Solanki |  |  |  | Remaining Work | Time of Tasks: | 30
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 30 | Ideal hrs/day: | 4.2857
0 | 2022-12-08 | 5 | 5 | 25 | 30
1 | 2022-12-09 | 5 | 5 | 20 | 25.7143
2 | 2022-12-10 | 5 | 5 | 15 | 21.4286
3 | 2022-12-11 | 5 | 5 | 10 | 17.1429
4 | 2022-12-12 |  |  | 10 | 12.8571
5 | 2022-12-13 |  |  | 10 | 8.5714
6 | 2022-12-14 |  |  | 10 | 4.2857
Faisal AlMuharrami |  |  |  | Remaining Work | Time of Tasks: | 14
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 14 | Ideal hrs/day: | 4.6667
0 | 2022-12-12 | 2 |  | 14 | 14
1 | 2022-12-13 |  |  | 14 | 9.3333
2 | 2022-12-14 |  |  | 14 | 4.6667
Tania Adame |  |  |  | Remaining Work | Time of Tasks: | 8
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 8 | Ideal hrs/day: | 1.3333
0 | 2022-12-08 | 0 | 0 | 8 | 8
1 | 2022-12-09 | 1 | 1 | 7 | 6.6667
2 | 2022-12-10 | 1 | 1 | 6 | 5.3333
3 | 2022-12-11 | 0 | 1 | 5 | 4
4 | 2022-12-12 | 4 | 3 | 2 | 2.6667
5 | 2022-12-13 | 2 | 2 | 0 | 1.3333
6 | 2022-12-14 | 4 | 3 | -3 | 0

## A.A. Template
Date
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Ideal hours per day and hours left
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Remaining Work | Time of Tasks: | 10 | Algorithmic Alchemist |  |  |  | Remaining Work | Time of Tasks: | 78
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 10 | Ideal hrs/day: | 1.4286 | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 78 | Ideal hrs/day: | 11.1429
0 | 2022-11-03 |  |  | 10 | 10 |  | 0 | 2022-11-03 | 0 | 0 | 78 | 78
1 | 2022-11-04 |  |  | 10 | 8.5714 |  | 1 | 2022-11-04 | 0 | 0 | 78 | 66.8571
2 | 2022-11-05 |  |  | 10 | 7.1429 |  | 2 | 2022-11-05 | 0 | 0 | 78 | 55.7143
3 | 2022-11-06 |  |  | 10 | 5.7143 |  | 3 | 2022-11-06 | 0 | 0 | 78 | 44.5714
4 | 2022-11-07 |  |  | 10 | 4.2857 |  | 4 | 2022-11-07 | 0 | 0 | 78 | 33.4286
5 | 2022-11-08 |  |  | 10 | 2.8571 |  | 5 | 2022-11-08 | 0 | 0 | 78 | 22.2857
6 | 2022-11-09 |  |  | 10 | 1.4286 |  | 6 | 2022-11-09 | 0 | 0 | 78 | 11.1429
David Chan |  |  |  | Remaining Work | Time of Tasks: | 20
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 20 | Ideal hrs/day: | 2.8571
0 | 2022-11-03 |  |  | 20 | 20
1 | 2022-11-04 |  |  | 20 | 17.1429
2 | 2022-11-05 |  |  | 20 | 14.2857
3 | 2022-11-06 |  |  | 20 | 11.4286
4 | 2022-11-07 |  |  | 20 | 8.5714
5 | 2022-11-08 |  |  | 20 | 5.7143
6 | 2022-11-09 |  |  | 20 | 2.8571
Bryant Lam |  |  |  | Remaining Work | Time of Tasks: | 16
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 16 | Ideal hrs/day: | 2.2857
0 | 2022-11-03 |  |  | 16 | 16
1 | 2022-11-04 |  |  | 16 | 13.7143
2 | 2022-11-05 |  |  | 16 | 11.4286
3 | 2022-11-06 |  |  | 16 | 9.1429
4 | 2022-11-07 |  |  | 16 | 6.8571
5 | 2022-11-08 |  |  | 16 | 4.5714
6 | 2022-11-09 |  |  | 16 | 2.2857
Abhay Solanki |  |  |  | Remaining Work | Time of Tasks: | 10
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 10 | Ideal hrs/day: | 1.4286
0 | 2022-11-03 |  |  | 10 | 10
1 | 2022-11-04 |  |  | 10 | 8.5714
2 | 2022-11-05 |  |  | 10 | 7.1429
3 | 2022-11-06 |  |  | 10 | 5.7143
4 | 2022-11-07 |  |  | 10 | 4.2857
5 | 2022-11-08 |  |  | 10 | 2.8571
6 | 2022-11-09 |  |  | 10 | 1.4286
Faisal AlMuharrami |  |  |  | Remaining Work | Time of Tasks: | 22
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | 22 | Ideal hrs/day: | 3.1429
0 | 2022-11-03 |  |  | 22 | 22
1 | 2022-11-04 |  |  | 22 | 18.8571
2 | 2022-11-05 |  |  | 22 | 15.7143
3 | 2022-11-06 |  |  | 22 | 12.5714
4 | 2022-11-07 |  |  | 22 | 9.4286
5 | 2022-11-08 |  |  | 22 | 6.2857
6 | 2022-11-09 |  |  | 22 | 3.1429