## Sprint 7 - Daily Standups
Sprint 7 Daily Stand-ups
2022-11-15 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | nothing | I will start coding authentication
David | No | I did not do anything yesterday. | I will create unit tests to cover core requirements for authentication.
Bryant | No |  | I will research error handling.
Abhay | No | Low Level Design for Authentication | Changes to LLD for Authentication
Faisal | no | nothing | BRD
Tania |  | Did not join yet | Did not join yet
2022-11-16 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Started coding Authentication validate password and username | Authenticate GenerateOTP and SqlAuthenticationDAO
David | No | I created the unit tests that covers the core requirements for authentications. | I will work on the authentication code.
Bryant | No | Researched Error handling | I will continue researching about error handling.
Abhay | No | Changes to LLD for Authentication | Finishing LLD for Authentication
Faisal | no | BRD | Input validation
Tania |  | Did not join yet | Did not join yet
2022-11-17 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Authenticate SqlAuthenticationDAO.cs and GenerateOTP function | Authentication Hash and UserProfile and UserAccount table in Database
David | No | I helped build AuthenticateUser, CheckOtpTimestamp, and generateOTP | I will change how the functions will work and create UserAuthenication model to make code easier.
Bryant | No | Researched Error handling | Seperate Scrum documents, add new sheets, integrate new member to the scrum documents
Abhay | No | Finished LLD for Authentication and had reivew meeting with Supervisor | Some changes to LLD for Authentication and starting LLD for Authorization
Faisal | no | research input validation | input validation for registration
Tania | no | Nothing | Read through groups project proposal
2022-11-18 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Authentication Hash and UserProfile and UserAccount table in Database | Authentication update code
David | No | I made created UserAuthentication and edit code to use Result model rather than booleans to add messages also. | I will make unit tests that will cover the core requirements for authorization.
Bryant | No | Seperated Scrum documents, Integrated new member to the scrum documents | Add error handing to authentication code
Abhay | No | Finished a draft one on LLD for Authorization | Making changes to draft one LLD for Authorization
Faisal | No | input validationm for registration | input validationm for registration
Tania | No | Added business rules to each case in the BRD | finish adding the business rules
2022-11-19 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Authentication update code | Authentication EncryptPassword, CreateSalt, an Regsistration CreateUserAccount
David | No | I created unit test for authorization that will cover the core requirements. | I will start code for Authentication.
Bryant | No | added error handling to authentication code | Add new scrum sheets for sprint planning and burndown charts
Faisal | NO | input validationm for registration | input validationm for registration
Tania | No | Adding business rules on the BRD | nothing
2022-11-20 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Authentication EncryptPassword, CreateSalt, an Regsistration CreateUserAccount | Authentication Encrypt Password, CreateSalt, and Registration CreateAccount
David | Yes | I started code for authentication but got stuck with using principal object. | I will help Abhay with changing the low level design for authentication
Bryant | No | Added new scrum sheets for sprint planning and burndown charts. | Work on LLD Registration and Authentication.
Faisal | no | input validationm for registration | help out with LLD
Tania | No | nothing | Helped implement the feedback
2022-11-21 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Authentication Encrypt Password, CreateSalt, and Registration CreateAccount | Work on LL design for authentication and BRD
David | No | I help change the Low Level Design for authentication. | I will use feedback from office hours to change the Low level design again.
Bryant | Yes | Got stuck working on LLD Registration and Authentication because I needed more knowledge on principal objects. | Research Authentication and principal objects.
Faisal | No | Helping with LLD | help with LLD
Tania | No | Helped implement the feedback to the BRD | BRD

## Sprint 8 - Daily Standups
Sprint 8 Daily Stand-ups
2022-11-22 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | work on the BRD use cases | work on LLD for authorization
David | Yes | I got stuck on figuring out what changes to the LLD to make so I instead switch to the HLD. | Im going to continue working on the HLD to allow the LLD to follow the HLD.
Bryant | Yes | Still stuck on LLD principal object, research principal object along with authentication. | I will work on HLD error handling using feedback from milestone 1.
Abhay | Yes | N/A | Reworking the Authentication LLD to adhere to SOLID
Faisal
Tania | No | Word on the BRD use cases | Finish up the use cases
2022-11-23 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | work on the LLD for authorization | work on LLD for authorization
David | No | I helped updated the high level design according to the feedback from the professor. | I will try to fix the session checking issue with the LLD for authenticaiton.
Bryant | Yes | Fixed error handling behavior in HLD using milestone 1 feedback. | Cannot do work because of other class assignments
Abhay | No | Reworked the authentication LLD to adhere to SOLID | Reworked the authorization LLD to adhere to SOLID
Faisal
Tania | No | Nothing | Finish added the use cases
2022-11-24 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | work on LLD for authorization | Thanksgiving break
David | No | I decided to create cookies and GenericIdentity to assist in checking the user seesion in the LLD. | Thanksgiving Break
Bryant | No | Blocked because of other class assignments | Thanksgiving Break
Faisal
Tania | No | Finishing up the BRD | Thanksgiving Break
2022-11-25 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Thanksgiving Break | Thanksgiving Break
David | No | Thanksgiving Break | Thanksgiving Break
Bryant | No | Thanksgiving Break | Thanksgiving Break
Faisal | No | Thanksgiving Break | Thanksgiving Break
Tania | No | Thanksgiving Break | Thanksgiving Break
2022-11-26 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Thanksgiving Break | Thanksgiving Break
David |  | Thanksgiving Break | Thanksgiving Break
Bryant | No | Thanksgiving Break | Thanksgiving Break
Abhay | No | N/A | Reworked Registration LLD to adere to SOLID
Faisal
Tania | No | Thanksgiving Break | Thanksgiving Break
2022-11-27 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Thanksgiving Break | Other class work
David |  | Thanksgiving Break | Thanksgiving Break
Bryant | No | Thanksgiving Break | Research more on domain models and application models
Abhay | No | Reworked Registration LLD to adere to SOLID | Reworking the HLD according to the feedback from the supervisor
Faisal | No | Thanksgiving Break | Thanksgiving Break
Tania | No | Thanksgiving Break | Thanksgiving Break
2022-11-28 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Other class work | Work on the BRD and seperate user cases
David | No | Thanksgiving Break | I will work on attempting to fix authentication LLD to better follow SOLID principles.
Bryant | No | Researched domain models and application models | Include specifics on domain and application models in HLD.
Abhay | Yes | Reworking the HLD according to the feedback from the supervisor | Reworking the HLD according to the feedback from the supervisor
Faisal | Yes | Nothing | Work on other classes
Tania | Yes | Nothing | work on assignments from other classes

## Sprint 9 - Daily Standups
Sprint 9 Daily Stand-ups
2022-11-29 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | work on the BRD and seperate the use cases | work on the BRD functional and nonfunctional requirements
David | Yes | I was able to make small changes to the LLD but not sure how to follow SOLID principles. | I will continue making changes to the authentication LLD
Bryant | No | Included domain and application models in HLD. | Look over HLD as a whole and fix or clarify any misconceptions.
Abhay | Yes | Finished reworking HLD | Starting rewriting BRD
Faisal | no | nothing | help with BRD and project plan
Tania | No | Worked on assignments from other classes | Finish up the BRD
2022-11-30 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | work on the BRD functional and nonfunctional requirements | work on the BRD seperating use cases
David | No | I made a few changes that I think will improve the flow and follow Solid better. | I will send in an email of the authentication LLD and start working on registration LLD.
Bryant | No | Touched up HLD | Update HLD from new feedback
Abhay | Yes | Submitted a BRD draft | Rewriting Authentication LLD according to supervisor feedback
Faisal | No | help with BRD and project plan | help with BRD and project plan
Tania | No | Help finish up the BRD | Make sure the BRD is finished and help on other areas that group needs help in.
2022-12-01 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | work on the BRD | Other class work
David | No | I sent in an email of the authentication LLD and started redoing the registration LLD. | Time off
Bryant | No | Updated HLD from new feedback | Nothing
Abhay | No | Rewriting Authentication LLD according to supervisor feedback | Rewriting Authorization LLD according to supervisor feedback
Faisal | No | help with BRD and project plan | help with BRD and project plan
Tania | No | help with the BRD | nothing
2022-12-02 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | Other class work | Work on the BRD
David | No | Time off | Time off
Bryant | Yes | Nothing | Completing a project from another class
Abhay | No | Rewriting Authorization LLD according to supervisor feedback | Rewriting Registration LLD according to supervisor feedback
Faisal | No | help with BRD and project plan | help with BRD and project plan
Tania | No | nothing | Do assignments from other class
2022-12-03 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | Time off | Time off
David | No | Time off | Time off
Bryant | No | Completed project from another class | Research DAR reports and Bill of Materials
Faisal | No | help with BRD and project plan | help with BRD and project plan
Tania | No | Do assignments from other class | Work on assisngment from another class
2022-12-04 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | Time off | Time off
David | No | I did nothing as I was out of town. | I will break down the project plan in more details including the testing and lld times.
Bryant | No | Researched DAR reports and Bill of Materials | Reformat HLD
Faisal | No | help with BRD and project plan | help with BRD and project plan
Tania | No | Work on other assignment from another class | help with BRD
2022-12-05 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Time off | Time off
David | No | I broke down the tasks into smaller parts in the project plan. | I will work on the project plan with faisal to fix issues the professor told us.
Bryant | Yes | Reformat HLD | Create presentation slides for another class.
Abhay | Yes | N/A | Researching ways of integration the Principal object into LLDs
Faisal | No | help with BRD and project plan | work on project plan
Tania | No | help with BRD | Research some ways to do the bill of materials
2022-12-06 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Time off | Finish up the BRD
David | No | I helped work on the project plan with faisal to fix some of the issues the professor told us. | I will assist in finishing up the BRD
Bryant | Yes | Blocked | Rehearse presentation for another class
Abhay | Yes | Sent another LLD draft to supervisor | Splitting use cases to follow feedback from the supervisor
Faisal | No | work on project plan | work on project plan
Tania | No | nothing | Research ways to format the bill of materials
2022-12-07 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | Work on the BRD | Finish up the BRD
David | No | I splited up a crime alerts and maintenance and renovation into better uses cases. | I will keep editing the BRD seperating more features and then adding more success and failure cases.
Bryant | No | Blocked | HLD, Project Plan, and fix scrum documents
Abhay | No | Added additional BRD use cases according to the feedback | Finish up the BRD
Faisal | No | work on project plan | work on project plan
Tania | Yes | research Bill of Materials format | Ask questions about the format

## Sprint 10 - Daily Standups
Sprint 10 Daily Stand-ups
2022-12-08 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | Work on the BRD | Work on the authorization LLD
David | No | I help finish the BRD by seperating features and adding more success and failure cases to each. | Unexpected busy day unable to work.
Bryant | Yes | HLD, Project Plan, and fix scrum documents | Resolve serious issues with professor in another class.
Abhay | No | Sent an BRD draft | Reworking Authentication LLD
Tania
2022-12-09 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Work on the authorization LLD | Work on the authorization LLD
David | No | Was unable to work. | I will start matching code to the registration code to the LLD.
Bryant | Yes | Started resolving serious issues in another class. | Finish resolving important issues in another class.
Abhay | No | Sent an draft for Authentication and Authorization LLD | Reworking Authorization LLD
Tania
2022-12-10 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Work on authorization LLD and research IIdentity and IPrincipal | work on LLD for authorization
David | Yes | I was having trouble with the code and decided to keep changing the LLD have a better flow. | I will work on the registration LLD and try to complete it.
Bryant | Yes | Finished resolving important issues in another class. | Research for my final paper from another class
Abhay | No | Sent another draft Authorizatino LLD | Reworking Registration LLD
Tania
2022-12-11 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | work on authorization LLD | work on authorization LLD
David | No | I completely redid the registration LLD as it had too many mistakes but was able to finish it. | I will work on all three LLDs while trying to follow the professors new advice.
Bryant | Yes | Researched information for my final paper from another class. | Complete my final paper from another class.
Abhay | No | Finished reworking Regisration LLD | Working on the rejected BRD
Faisal | No | N/A(remove) | N/A(remove)
Tania | No | Asked about how the format of the BoM should be | Work on the rejected BRD
2022-12-12 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | Yes | work on LLD authorization | Finsh authorization LLD
David | No | I worked with Sierra and Abhay to make big changes to each LLD and then we emailed it for review. | I will reorganize code and finsh matching registration code to registration LLD.
Bryant | Yes | Complete my final paper from another class. | Work on LLD Registration and fix scrum documents
Abhay | No | Worked on BRD | Coding Tests for Authentication
Faisal | no | nothing | work on bill of materials
Tania | No | Get started on the BoM | Work on bill of materials
2022-12-13 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Tania
2022-12-14 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Tania