## Sprint Planning 7
Sprint Planning
Sprint 7: 11/15/22 - 11/21/22
Work Item(s) |  |  | Estimated Work Hours to Complete |  |  | Total Work Hours
Body Core Requirements |  |  | 20 |  |  | 135
Testing |  |  | 35
Libraries: Input Validation & Error Handling |  |  | 25
LL Design |  |  | 35
Libraries: Input Validation & Error Handling |  |  | 20
Member: | Abhay | David | Sierra | Faisal | Bryant | Tania
Task(s): | LL Design | LL Design Unit Test | Code AuthN & AuthZ | Libraries | Libraries | LL Design & BRD
Est Time: | 18 | 24 | 40 | 20 | 21 | 12
2022-11-15 | 6 | 3 | 7 | 4 | 3 | 0
2022-11-16 | 4 | 6 | 6 | 3 | 4 | 0
2022-11-17 | 6 | 3 | 7 | 4 | 6 | 4
2022-11-18 | 4 | 3 | 7 | 3 | 6 | 2
2022-11-19 | 0 | 7 | 5 | 4 | 2 | 3
2022-11-20 | 0 | 7 | 7 | 3 | 2 | 2
2022-11-21 | 0 | 3 | 6 | 1 | 2 | 4
Individual Capacity | 20 | 32 | 45 | 22 | 25 | 15
Team Total Capaciy
159
Total Est. Workload
135
Extra Team Capacity Time
24

## Sprint Planning 8
Sprint Planning
Sprint 8: 11/22/22 - 11/28/22
Work Item(s) |  |  | Estimated Work Hours to Complete |  |  | Total Work Hours
HLD |  |  | 25 |  |  | 65
LL Design |  |  | 30
BRD |  |  | 10
Member: | Abhay | David | Sierra | Faisal | Bryant | Tania
Task(s): | LL Design & HLD | LL Design & HLD | LL Design & BRD | LL Design & HLD | HLD | LL Design & BRD
Est Time: | 18 | 10 | 12 | 8 | 8 | 9
2022-11-22 | 4 | 3 | 6 | 4 | 3 | 3
2022-11-23 | 4 | 7 | 6 | 4 | 0 | 1
2022-11-24 | 0 | 0 | 0 | 2 | 0 | 0 | Thanksgiving
2022-11-25 | 0 | 0 | 0 | 0 | 0 | 0 | Thanksgiving
2022-11-26 | 4 | 0 | 0 | 0 | 0 | 0 | Thanksgiving
2022-11-27 | 4 | 0 | 0 | 0 | 3 | 2 | Thanksgiving
2022-11-28 | 4 | 3 | 2 | 0 | 4 | 2
Individual Capacity | 20 | 13 | 14 | 10 | 10 | 8
Team Total Capaciy
75
Total Est. Workload
65
Extra Team Capacity Time
10

## Sprint Planning 9
Sprint Planning
Sprint 9: 11/29/22 - 12/7/22
Work Item(s) |  |  | Estimated Work Hours to Complete |  |  | Total Work Hours
BRD Core Requirements |  |  | 40 |  |  | 120
LL Design |  |  | 50
Project plan |  |  | 30
Member: | Abhay | David | Sierra | Faisal | Bryant | Tania
Task(s): | HLD and BRD | LLD & PP & BRD | LL Design & BRD | LL Design & HLD | LL Design | LL Design & BRD
Est Time: | 25 | 18 | 35 | 20 | 12 | 10
2022-11-29 | 5 | 3 | 7 | 1 | 2 | 0
2022-11-30 | 5 | 5 | 6 | 3 | 3 | 2
2022-12-01 | 5 | 0 | 7 | 2 | 0 | 1
2022-12-02 | 5 | 0 | 3 | 2 | 0 | 2
2022-12-03 | 0 | 0 | 0 | 2 | 3 | 2
2022-12-04 | 0 | 1 | 0 | 2 | 1 | 1
2022-12-05 | 6 | 6 | 0 | 4 | 0 | 1
2022-12-06 | 6 | 3 | 7 | 2 | 0 | 2
2022-12-07 | 6 | 6 | 7 | 6 | 5 | 1
Individual Capacity | 38 | 24 | 37 | 24 | 14 | 12
Team Total Capaciy
149
Total Est. Workload
120
Extra Team Capacity Time
29

## Sprint Planning 10
Sprint Planning
Sprint 10: 12/8/22 - 12/14/22
Work Item(s) |  |  | Estimated Work Hours to Complete |  |  | Total Work Hours
Testing |  |  | 25 |  |  | 95
Libraries: Input Validation & Error Handling |  |  | 20
LL Design |  |  | 20
Libraries: Input Validation & Error Handling |  |  | 20
Bill of Materials |  |  | 10
Member: | Abhay | David | Sierra | Faisal | Bryant | Tania
Task(s): | LL Design & Code | Coding & LLD | LL Design & BRD | Code & LLD & HLD | LL Design | LL Design & BRD
Est Time: | 30 | 25 | 10 | 14 | 8 | 8
2022-12-08 | 5 | 3 | 6 |  | 0 | 2
2022-12-09 | 5 | 3 | 6 |  | 0 | 1
2022-12-10 | 5 | 3 | 0 |  | 0 | 0
2022-12-11 | 5 | 6 | 0 |  | 0 | 0
2022-12-12 | 5 | 6 | 0 | 4 | 4 | 1
2022-12-13 | 5 | 3 | 0 | 5 | 2 | 2
2022-12-14 | 5 | 4 | 2 | 5 | 4 | 3
Individual Capacity | 35 | 28 | 14 | 14 | 10 | 9
Team Total Capaciy
110
Total Est. Workload
95
Extra Team Capacity Time
15