## A.A Sprint Retrospectives
Sprint 7 Retrospective
11/15/22 - 11/21/22 | Did you finish? | What did you do well? | What went wrong during the sprint?
Sierra | No | coding registration, authentication and authorization | Sprint planning of the work items
David | No | I think I did well with coding and creating tests | I was not able to build code as our low level design was not built well enough.
Bryant | No | Created simple error handling for AuthN. | Resolving specific error handling cases was not possible until code was done.
Abhay | Yes | Created a LLD for Authentication and Authorization | Did not have enough knowledge on SOLID principal and Principal library, to make a good LLD
Faisal | yes | Created a input validation class for registration | got burnt out
Tania | Yes | Was able to add the succes and failure cased for the BRD | Ask more questions about how the BRD should be formatted.
11/15/22 - 11/21/22 | If not finished what were the tasks that are uncompleted? |  | What can you do better? What actions are you going to take on future sprints to solve these problems?
Sierra | The LLD designs for authorization, and authentication |  | Finish work items instead of just working on them.
David | We did not finish the LLD as we planned. |  | I need to figure out how to better design LLD.
Bryant | Error handling for Registration and AuthZ were not completed. |  | Need to understand what to complete first and make sure it is correct because the work items builds off of them.
Abhay | N/A |  | More communication with the supervisor and research
Faisal | N/A |  | Be more efficient with managing my time and formatting code better
Tania
Sprint 8 Retrospective
11/22/22 - 11/28/22 | Did you finish? | What did you do well? | What went wrong during the sprint?
Sierra | No | Work on the BRD and add core requirements and feedback | Did not finish updating the BRD
David | No | I was able to make good progress with the HLD. | We had little time due to thanksgiving trip and had trouble following SOLID.
Bryant | Yes | Fixed mistakes on HLD based on feedback. | Got stuck on principal and identities in LLD.
Abhay | No | Worked on LLD and HLD | There were several times we needed to rework LLD, which was not very effective
Faisal | No | Helped with the BRD and LLD | finding out if we were right or wrong before moving forward
Tania | Yes | Worked BRD added things that we didn't do the first time in the BRD
11/22/22 - 11/28/22 | If not finished what were the tasks that are uncompleted? |  | What can you do better? What actions are you going to take on future sprints to solve these problems?
Sierra | BRD and LLDs for authentication and authorization |  | Get feedback on LLD and BRD earlier to fix them. Going to start requesting feedback sooner
David | The LLD parts that I was assigned was not finished. |  | I will try to ask the professor more questions about SOLID to figure out how to better implement it.
Bryant | Task from sprint 7 were not completed which were still not finished in this sprint. |  | Need more research to understand our capacities and what work items we can handle.
Abhay | Could not complete HLD according to supervisor feedback because of lack of knowledge |  | Frequent reworking of LLDs decreased available work hour for other work items. It was all due a misunderstanding of a feedback from the supervisor. Better communication for effective reworking of work items.
Faisal | didnt finish BRD |  | Ask more questions and ask for help from the team
Tania |  |  | Ask more questions
Sprint 9 Retrospective
11/29/22 - 12/7/22 | Did you finish? | What did you do well? | What went wrong during the sprint?
Sierra | Yes | Work on the BRD and seperate the use cases | did not finish the LLD for authorization
David | Yes | I did lots of work on the BRD and decent help witht the project plan. | Not much went wrong except i should have spent more time on the project plan to add mroe details.
Bryant | Yes | Cleared up many errors in the HLD. | Nothing got in the way of completing the HLD
Abhay | Yes | Reworking LLDs and BRD with feedback and effective reworks | Nothing got in the way of working this sprint
Faisal | Yes | Helped with BRD and finished up Project plan | I didnt account for research time when making proejct plan
Tania | Yes | Helped with the BRD | Finish sooner so we can implement the feedback on time in case something went wrong
11/29/22 - 12/7/22 | If not finished what were the tasks that are uncompleted? |  | What can you do better? What actions are you going to take on future sprints to solve these problems?
Sierra | Finished the BRD but not the LLD |  | Going to start assigning deadlines to make sure things get done timely and not last minute
David | None, we finished the BRD and Project plan. |  | Having more time in the future sprint by not having anymore family trips out of town.
Bryant | N/A |  | Send HLD more often to get more feedback.
Abhay | N/A |  | I think my performance was satifactory
Faisal | N/A |  | I give myself a pat on the back
Tania |  |  | I can ask more questions to the professor instead of sending BRDs
Sprint 10 Retrospective
12/8/22 - 12/14/22 | Did you finish? | What did you do well? | What went wrong during the sprint?
Sierra
David
Bryant
Abhay
Faisal
Tania
12/8/22 - 12/14/22 | If not finished what were the tasks that are uncompleted? |  | What can you do better? What actions are you going to take on future sprints to solve these problems?
Sierra
David
Bryant
Abhay
Faisal
Tania