## Project Backlog
PROJECT BACKLOG
Work item | Type | Description | Priority | Effort (hr)
Milestone 3 | Epic | As a developer, I can read logs, change permissions, allow users to recover their account, and understand what technologies are needed to create the product. |  | 176
Authentication | User Story | As a developer, I can identify which user is trying to use some feature. | 1 | 64
Authorization | User Story | As a developer, I can change the permissions of access. | 2 | 64
Registration | User Story | As a user, I can register for a new account. | 3 | 32
Bill of Materials | User Story | As a developer, I understand what technologies were used to create this product. | 4 | 16
HLD Renovations | Epic |  |  | 32
Project Plan Renovations | Epic |  |  | 16
BRD Renovations | Epic |  |  | 32
Archiving | User Story
Account Recovery | User Story
Archiving | User Story | As a user, I can get my account back if I forget my credentials. |  | 32
Project Proposal | User Story | As a developer, I would like to see the values and features of the product | 1 | 19.5
PP Features | Split Story | As a developer, I want to know what features will connect with the value | 1.1 | 6
PP User Needs | Split Story | As a developer, I want to know who the target audience is | 1.2 | 2
PP Proposed Solution | Split Story | As a developer, I want to know how the product will fix the problem | 1.3 | 2
PP Future Vision | Split Story | As a developer, I want to know the possible scalability of the product | 1.4 | 2
PP Product Scope | Split Story | As a developer, I want to know the complexity of the product | 1.45 | 1.5
PP Project Scope | Split Story | As a developer, I want to know the complexity of the project | 1.5 | 1.5
PP About Project | Split Story | As a developer, I want to know what the product is | 1.6 | 1
PP Abstract | Split Story | As a developer, I would like to get a summary of the product | 1.65 | 1
PP Competitors | Split Story | As a developer, I would like to know who has created a similar product and if they are successful | 1.7 | 1
PP References | Split Story | As a developer, I would like to see the references for information | 1.8 | 0.5
PP Glossary | Split Story | As a developer, I would like to see the meaning of words to understand the same language | 1.9 | 1
Milestone 1 | Epic | As a client, I can understand the Project details, values, and deadlines through the Business Requirement Document, Project Plan, and High Level Design. | 1 | 96
Business Req. Document | User Story | As a client, I would like to see the FRQs, NFRQs, and Business Rules. | 2 | 64
BRD NFRQ and FRQ | Split Story | As a client, I want to understand the function and non-functional requirements for the features. | 2.1 | 16
BRD Business Rules | Split Story | As a developer, I understand my client's business rules that will make the feature successful. | 2.2 | 16
BRD Business Requirements | Split Story | As a client, I want to understand the business requirements. | 2.3 | 8
BRD Success Factors | Split Story | As a client, I want to know what will criterias make the features successful. | 2.4 | 6
BRD Failures | Split Story | As a client, I want to know how failures are resolved. | 2.5 | 4
BRD Business Goal | Split Story | As a client, I want to understand the goal of this product. | 2.6 | 2
BRD Project Overview | Split Story | As a client, I want to understand the product from the developer's POV. | 2.7 | 4
BRD Overview | Split Story | As a client, I want to understand what is inside the document. | 2.8 | 4
BRD Project Constraints | Split Story | As a client, I want to know the constraints of the product. | 2.9 | 2
Stakeholder Identification | Split Story | As a client, I want to know who is involved and will benefit from this product. | 2.95 | 2
Project Plan | User Story | As a developer, I would like to see the day-by-day progress of each work item. | 3 | 16
Project Roadmap | Split Story | As a client, I would like to see the date of completion for features. | 3.1 | 4
High Level Design | User Story | As a developer, I can understand the significance of each features and how they work with everything else. | 4 | 16
Milestone 2 | Epic | As a developer, I can understand the Network diagram, LL design, logs, and allow users to register for an account. |  | #REF!
Logging | User Story | As a developer, I can read logs to understand what is being computed. | 2 | 64
LL Design for Logging and Registration | User Story | As a developer, I can understand how the flow through abstract layers within Registration and Logging functionalities. | 3 | 64
Network Diagram | User Story | As a developer, I understand what task and components require network and how it flows. | 4 | 32