## Project Backlog
PROJECT BACKLOG
Work item | Type | Description | Priority | Effort
Project Proposal | User Story | As a developer, I would like to see the values and features of the product | 1 | 19.5
PP Features | Split Story | As a developer, I want to know what features will connect with the value | 1.1 | 6
PP User Needs | Split Story | As a developer, I want to know who the target audience is | 1.2 | 2
PP Proposed Solution | Split Story | As a developer, I want to know how the product will fix the problem | 1.3 | 2
PP Future Vision | Split Story | As a developer, I want to know the possible scalability of the product | 1.4 | 2
PP Product Scope | Split Story | As a developer, I want to know the complexity of the product | 1.45 | 1.5
PP Project Scope | Split Story | As a developer, I want to know the complexity of the project | 1.5 | 1.5
PP About Project | Split Story | As a developer, I want to know what the product is | 1.6 | 1
PP Abstract | Split Story | As a developer, I would like to get a summary of the product | 1.65 | 1
PP Competitors | Split Story | As a developer, I would like to know who has created a similar product and if they are successful | 1.7 | 1
PP References | Split Story | As a developer, I would like to see the references for information | 1.8 | 0.5
PP Glossary | Split Story | As a developer, I would like to see the meaning of words to understand the same language | 1.9 | 1
Milestone 1 | Epic | As a client, I can understand the Project details, values, and deadlines through the Business Requirement Document, Project Plan, and High Level Design. | 1 | 96
Business Req. Document | User Story | As a client, I would like to see the FRQs, NFRQs, and Business Rules. | 2 | 64
BRD NFRQ and FRQ | Split Story | As a client, I want to understand the function and non-functional requirements for the features. | 2.1 | 16
BRD Business Rules | Split Story | As a developer, I understand my client's business rules that will make the feature successful. | 2.2 | 16
BRD Business Requirements | Split Story | As a client, I want to understand the business requirements. | 2.3 | 8
BRD Success Factors | Split Story | As a client, I want to know what will criterias make the features successful. | 2.4 | 6
BRD Failures | Split Story | As a client, I want to know how failures are resolved. | 2.5 | 4
BRD Business Goal | Split Story | As a client, I want to understand the goal of this product. | 2.6 | 2
BRD Project Overview | Split Story | As a client, I want to understand the product from the developer's POV. | 2.7 | 4
BRD Overview | Split Story | As a client, I want to understand what is inside the document. | 2.8 | 4
BRD Project Constraints | Split Story | As a client, I want to know the constraints of the product. | 2.9 | 2
Stakeholder Identification | Split Story | As a client, I want to know who is involved and will benefit from this product. | 2.95 | 2
Project Plan | User Story | As a developer, I would like to see the day-by-day progress of each work item. | 3 | 16
Project Roadmap | Split Story | As a client, I would like to see the date of completion for features. | 3 | 4
High Level Design | User Story | As a developer, I can understand the significance of each features and how they work with everything else. | 4 | 16
Milestone 2 | Epic | As a developer, I can understand the Network diagram, LL design, logs, and allow users to register for an account. | 2 | 192
Network Diagram | User Story | As a developer, I understand what task and components require network and how it flows. | 2.1 | 32
LL Design | User Story | As a developer, I can understand how each feature will trigger and how it works. | 2.2 | 64
Registration | User Story | As a user, I can register for a new account. | 2.3 | 32
Logging | User Story | As a developer, I can read logs to understand what is being computed. | 2.4 | 64
Milestone 3 | Epic | As a developer, I can read logs, change permissions, allow users to recover their account, and understand what technologies are needed to create the product. | 3 | 176
Authentication | User Story | As a developer, I can identify which user is trying to use some feature. | 3.1 | 64
Authorization | User Story | As a developer, I can change the permissions of access. | 3.2 | 64
Account Recovery | User Story | As a user, I can get my account back if I forget my credentials. | 3.3 | 32
Bill of Materials | User Story | As a developer, I understand what technologies were used to create this product. | 3.4 | 16
User Profile | User Story | As a user, I can see my account history and ratings from services. | 4 | 80
View History | Split Story | As a user, I can view my account history. | 4.1 | 32
View Rating | Split Story | As a user, I can see my ratings from past services. | 4.2 | 32
Dashboard | User Story | As a user, I can modify or update appoinments. | 5 | 84
View Rating | Split Story | As a user, I can view my ratings. | 5.1 | 16
View Upcoming Appointment | Split Story | As a user, I can view my future appointments. | 5.2 | 16
View Property Value | Split Story | As a user, I can view my property value. | 5.3 | 36
DIY Project Manager | User Story | As a user, I can assign a time on a calendar to work on DIY tutorials and post them. | 6 | 80
Upload DIY | Split Story | As a user, I can upload a post. | 6.1 | 16
Save DIY | Split Story | As a user, I can save a post. | 6.2 | 16
Calendar | User Story | As a user, I can show all available days and schedule appointments on a calendar. | 7 | 80
Schedule Appointment | Split Story | As a user, I can schedule an appointment. | 7.1 | 32
Modify / Delete Appointment | Split Story | As a user, I can change or delete appointments. | 7.2 | 16
View Appointments | Split Story | As a user, I can view all appointments. | 7.3 | 16
User Management | User Story | As a user, I can create, delete, and recover my account. | 8 | 64
Service Management | User Story | As a user, I can look up services with their ratings and sign contracts with them. | 9 | 128
Service Request | Split Story | As a user, I can request a service. | 9.1 | 48
Frequency Change/Cancellation | Split Story | As a user, I can request to cancel a service. | 9.2 | 32
Service Rating | Split Story | As a user, I can see the service ratings. | 9.3 | 20
Request Management | User Story | As a user, I can view and complete request from other users. | 10 | 96
View Request | Split Story | As a user, I can view request. | 10.1 | 32
Update Service | Split Story | As a user, I can update a request. | 10.2 | 32
Service Rating | Split Story | As a user, I can see the service ratings. | 10.3 | 16
Property Evaluation | User Story | As a user, I can request property walk-throughs and get an estimated value of the property. | 11 | 48
Evaluate Property | Split Story | As a user, I can get an estimated value of the property. | 11.1 | 32
Maintenance and Renovation | User Story | As a user, I can answer questions using pre-determined answers to help with budgeting maintenance and renovation. | 12 | 80
Comparing | Split Story | As a user, I can compare cost of maintenance and renovations options. | 12.1 | 16
Estimating | Split Story | As a user, I can see an estimation of the cost for maintenance and renovations. | 12.2 | 16
Smart Saver | Split Story | As a user, I can see a price history of raw materials. | 12.3 | 32
Neighborhood Crime Alerts | User Story | As a user, I can access the Crime Alert map and enable notifications for reported crime. | 13 | 112
Add Crime Alerts | Split Story | As a user, I can report a crime. | 13.1 | 64
Edit/Delete Crime Alerts | Split Story | As a user, I can delete/edit my reports. | 13.2 | 16
Document Storage with Optical Text Search | User Story | As a user, I can store, search, and share my documents. | 14 | 80
Optical Text Seach | Split Story | As a user, I can search for my document. | 14.1 | 32
Upload Document | Split Story | As a user, I can upload and share my documents. | 14.2 | 16
Sign Document | Split Story | As a user, I can sign a document. | 14.3 | 16

## Sprint Planning
Sprint Planning
Sprint 2: 9/30 - 10/5 | Work item(s)
Sierra Harris | BRD, Project Plan, and HL Design
David Chan | Project Plan and BRD
Bryant Lam | BRD
Abhay Solanki | BRD and HL Design
Faisal AlMuharrami | BRD and HL Design
Kevin Thai
Sprint 3 TBD | Work item(s)
Sierra Harris
David Chan
Bryant Lam
Abhay Solanki
Faisal AlMuharrami
Kevin Thai

## A.A. Sprint 0
Leave Day 0 empty.
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Don't change this column
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0 | Algorithmic Alchemist
0 | 2022-09-16 |  | 2 | -2 |  |  | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
1 | 2022-09-17 |  | 3 | -5 |  |  | 0 | 2022-09-16 | 0 | 2 | 0
2 | 2022-09-18 |  | 0 | -5 |  |  | 1 | 2022-09-17 | 3 | 12 | -12
3 | 2022-09-19 |  | 0 | -5 |  |  | 2 | 2022-09-18 | 0 | 0 | -12
4 | 2022-09-20 |  | 4 | -9 |  |  | 3 | 2022-09-19 | 0 | 0 | -12
5 | 2022-09-21 |  | 3 | -12 |  |  | 4 | 2022-09-20 | 3 | 13 | -25
6 | 2022-09-22 |  | 2 | -14 |  |  | 5 | 2022-09-21 | 0 | 3 | -28
[7 empty] | 6 | 2022-09-22 | 0 | 2 | -30
Abhay Solanki
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-16 |  | 0 | 0
1 | 2022-09-17 | 3 | 3 | -3
2 | 2022-09-18 |  | 0 | -3
3 | 2022-09-19 |  | 0 | -3
4 | 2022-09-20 | 3 | 3 | -6
5 | 2022-09-21 |  | 0 | -6
6 | 2022-09-22 |  | 0 | -6
Faisal AlMuharrami
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-16 |  | 0 | 0
1 | 2022-09-17 |  | 3 | -3
2 | 2022-09-18 |  | 0 | -3
3 | 2022-09-19 |  | 0 | -3
4 | 2022-09-20 |  | 3 | -6
5 | 2022-09-21 |  | 0 | -6
6 | 2022-09-22 |  | 0 | -6
Kevin Thai
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-16 |  | 0 | 0
1 | 2022-09-17 |  | 3 | -3
2 | 2022-09-18 |  | 0 | -3
3 | 2022-09-19 |  | 0 | -3
4 | 2022-09-20 |  | 3 | -6
5 | 2022-09-21 |  | 0 | -6
6 | 2022-09-22 |  | 0 | -6

## A.A. Sprint 1
Leave Day 0 empty.
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Don't change this column
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0 | Algorithmic Alchemist
0 | 2022-09-23 |  | 0 | 0 |  |  | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
1 | 2022-09-24 |  | 5 | -5 |  |  | 0 | 2022-09-23 | 0 | 0 | 0
2 | 2022-09-25 |  | 0 | -5 |  |  | 1 | 2022-09-24 | 0 | 8 | -8
3 | 2022-09-26 |  | 2 | -7 |  |  | 2 | 2022-09-25 | 0 | 0 | -8
4 | 2022-09-27 |  | 2 | -9 |  |  | 3 | 2022-09-26 | 0 | 2 | -10
5 | 2022-09-28 |  | 0 | -9 |  |  | 4 | 2022-09-27 | 0 | 4 | -14
[7 empty] | 5 | 2022-09-28 | 0 | 0 | -14
Abhay Solanki
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-23 |  | 0 | 0
1 | 2022-09-24 |  | 0 | 0
2 | 2022-09-25 |  | 0 | 0
3 | 2022-09-26 |  | 0 | 0
4 | 2022-09-27 |  | 0 | 0
5 | 2022-09-28 |  | 0 | 0
Faisal AlMuharrami
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-23 |  | 0 | 0
1 | 2022-09-24 |  | 3 | -3
2 | 2022-09-25 |  | 0 | -3
3 | 2022-09-26 |  | 0 | -3
4 | 2022-09-27 |  | 1 | -4
5 | 2022-09-28 |  | 0 | -4
Kevin Thai
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-23 |  | 0 | 0
1 | 2022-09-24 |  | 0 | 0
2 | 2022-09-25 |  | 0 | 0
3 | 2022-09-26 |  | 0 | 0
4 | 2022-09-27 |  | 1 | -1
5 | 2022-09-28 |  | 0 | -1

## A.A. Sprint 2
Leave Day 0 empty.
Total Hours Spent
Hours of Productivity: Input Hours worked.
Remaining Work: Displays remaining work hours using difference between hours worked and time of tasks.
Time of Task: Input Estimated Effort(in hrs) from Project Backlog
Sierra Harris |  |  |  | Don't change this column
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: |  | Algorithmic Alchemist
0 | 2022-09-29 |  | 2 | -2 |  |  | Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 8
1 | 2022-09-30 |  | 2 | -4 |  |  | 0 | 2022-09-29 | 5 | 3 | 8
2 | 2022-10-01 |  | 3 | -7 |  |  | 1 | 2022-09-30 | 7.5 | 4 | 4
3 | 2022-10-02 |  | 4 | -11 |  |  | 2 | 2022-10-01 | 12 | 5 | -1
4 | 2022-10-03 |  | 2 | -13 |  |  | 3 | 2022-10-02 | 11.5 | 8 | -9
5 | 2022-10-04 |  | 4 | -17 |  |  | 4 | 2022-10-03 | 14 | 9 | -18
6 | 2022-10-05 |  | 4 | -21 |  |  | 5 | 2022-10-04 | 16 | 12.5 | -30.5
[7 empty] | 5 | 2022-10-05 | 11.5 | 9 | -39.5
David Chan
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks:
0 | 2022-09-29 | 4 | 0 | 0
1 | 2022-09-30 | 2.5 | 0 | 0
2 | 2022-10-01 | 6 | 0 | 0
3 | 2022-10-02 | 1.5 | 0 | 0
4 | 2022-10-03 | 4 | 0 | 0
5 | 2022-10-04 | 4 | 0 | 0
6 | 2022-10-05 | 6.5 | 0 | 0
Bryant Lam
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 8
0 | 2022-09-29 |  | 0 | 8
1 | 2022-09-30 | 2 | 1 | 7
2 | 2022-10-01 |  | 0 | 7
3 | 2022-10-02 | 3 | 1 | 6
4 | 2022-10-03 | 2 | 1 | 5
5 | 2022-10-04 | 4 | 3 | 2
6 | 2022-10-05 | 3 | 3 | -1
Abhay Solanki
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-29 |  | 0 | 0
1 | 2022-09-30 |  | 0 | 0
2 | 2022-10-01 | 2 | 1 | -1
3 | 2022-10-02 | 2 | 1 | -2
4 | 2022-10-03 | 5 | 4 | -6
5 | 2022-10-04 | 6 | 4.5 | -10.5
6 | 2022-10-05 |  | 0 | -10.5
Faisal AlMuharrami
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks:
0 | 2022-09-29 | 1 | 1 | -1
1 | 2022-09-30 | 1 | 1 | -2
2 | 2022-10-01 | 2 | 1 | -3
3 | 2022-10-02 | 5 | 2 | -5
4 | 2022-10-03 | 3 | 2 | -7
5 | 2022-10-04 | 2 | 1 | -8
6 | 2022-10-05 | 2 | 2 | -10
Kevin Thai
Sprint Length(Days) | Date | Total Hours Spent | Hours of Productivity | Remaining Work | Time of Tasks: | 0
0 | 2022-09-29 |  | 0 | 0
1 | 2022-09-30 | 2 | 0 | 0
2 | 2022-10-01 | 2 | 0 | 0
3 | 2022-10-02 |  | 0 | 0
4 | 2022-10-03 |  | 0 | 0
5 | 2022-10-04 |  | 0 | 0
6 | 2022-10-05 |  | 0 | 0

## Daily Stand-ups 0-2
Daily Stand-ups Sprint 0
2022-09-20 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | project proposal | project propsal
David | No | I started second version of the RFP and created an outline for it along with some new features. | I am adding more features into RFP and will create the project the project scope and software sections.
Bryant | No | Researched examples of BRDs | I will create the Project Backlog and work on Project Proposal Features
Abhay
Faisal
Kevin
2022-09-21 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | future features | work on project proposal vision
David | No | I added more features into RFP and created project scope and software sections. | I am going to research features and work on PP Features.
Bryant | No | I created the Project Backlog and worked on Project Proposal Features | I am going to work on the PP Competitors and PP User Needs
Abhay
Faisal
Kevin
2022-09-22 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | vision | Work on proposal future features
David | No | I added new features and edited other features to fit a theme. | I am working on PP Abstract and PP Proposed Solution.
Bryant | No | I completed the PP User Needs and worked on PP Competitors | I am going to continue working on PP Competitors and create the BRD Framework/Template
Abhay |  | Added a new feature: Document Storage with Optical Text Search, added 2D drafting, and Mobile Optimization in Vision.
Faisal
Kevin
2022-09-23 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Worked on the proposal | Nothing
David | No | I completed PP Abstract and PP Proposed Solution. | I am working on researching new ideas for features.
Bryant | No | I completed PP Competitors and worked on the BRD Framework/Template | I am going to complete the BRD Template and work on BRD Overview
Abhay
Faisal
Kevin
2022-09-24 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Nothing | Work on the proposal features
David | No | I thought of 3 new ideas of playdates, puppy growth collage, and to improve pet profile with medical records. | I am going to implement the new ideas and edit other features to align better with our value.
Bryant
Abhay
Faisal | No | Reworked the proposal | rework the proposal
Kevin
2022-09-25 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | work on propsal features | Nothing
David | No | I added 3 new ideas and edited some features to make it follow the value of the project better. | I am not going to do anything today due to feeling unwell.
Bryant
Abhay
Faisal
Kevin
Daily Stand-ups Sprint 1
2022-09-26 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Nothing | Outline for BRD and HLDesign, Enviroment set up
David | No | I did not do anything yesterday. | I will be attempting to fix the product features of the RFP.
Bryant | No |  | I am going to refine PP Features.
Abhay
Faisal | no | N/A | N/A
Kevin
2022-09-27 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Outline for BRD and HL Design | Work on proposal version 5
David | No | I fixed the features for interactive petcam, pet sitting services, pet care services, and I also did a small part of future plans. | I will change how pet profiles and playdate will work and will add more future plans
Bryant | No | I worked on PP Features | I will add more features to PP Features
Abhay
Faisal | no | N/A | Research regarding Milestone 1 (no work to be done)
Kevin
2022-09-28 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Work on proposal 5 | Nothing
David | No | I changed how pet profile and playdate works and added future plans improvement to playdate, livechat reactive sounds, and pet profiles. | I will review and edit the RFP to get it ready to submit the version 3 for approval.
Bryant | No | I worked on PP Features | I will work on BRD Use Cases
Abhay
Faisal | No | Research regarding Milestone 1 (no work to be done) | work on proposal until its approved
Kevin
2022-09-29 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | I worked on the proposal v5 | work on proposal version 6
David | No | I completed the next draft of the RFP to send to the professor but our team was scrapped and entered into a new team. I also reviewed and research for new features to add. | I am going to add new features to the RDP and Start on BRD functional requirements.
Bryant
Abhay
Faisal | no | I worked on proposal v5 | get ready to revise new proposal in case not approved and do research about HLD and some work on it
Kevin
Daily Stand-ups Sprint 2
2022-09-30 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | I worked on the project proposal version 7 | Work on the BRD functional and nonfuctional requirements section
David | No | I added 3 new features to the RFP and 1 feature for the future plans. | I will fix the features in RFP and begin working on BRD.
Bryant | No |  | I will work on functional requirements in the BRD
Abhay
Faisal | No | researched data flow diagrams and worked on HLD | draw some diagrams in preparation
Kevin |  |  | Work on functional requirements in the BRD
2022-10-01 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Work on the BRD functional and nonfucntional requirements section | Work on BRD failure and success cases
David | No | I removed 2 features, edit 1 feature, and added a new feature to RFP and I finished 3 feature Functional requirements. | I will work on finishing the rest of the funtional requirements for the BRD and start on the non-functional requirements.
Bryant
Abhay
Faisal | no | drew some diagrams | make sure we have what we need in BRD and proof read
Kevin |  | I worked on Functional Requirements in the BRD | Research BRD and work on functional requirements
2022-10-02 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | worked on the BRD failure and success cases | work on HL Design and project plan
David | No | I finished up all the functional requirements left for BRD and made some non-functional requirements for 3 of the features. | I will create the project plan outline and make adjustments to some functional and non functional requirements to make it more easier to understand.
Bryant | No |  | I worked on HL Design and BRD Overviews
Abhay | No | Worked on some Functional Requirements in BRD | Going to switch focus to High Level Desgin, and research.
Faisal | No | helped finish up BRD | split up to work with abhay in HLD and research and discussion
Kevin | No | Additional Research in the BRD and work on functional requirements | No work. Spend the day studying for midterms
2022-10-03 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | no | worked on HLD architectural diagram, BRD sucess and failure cases | Work on BRD and HLD
David | No | I created the project plan outline and make adjustments to some functional and non functional requirements to make it more easier to understand. | I will try to work with the team to estimate times for each task to finish up the project plan.
Bryant | No | I worked on HL Design and BRD Overviews. | I will work on the BRD NFRQ and FRQ
Abhay | No | Worked on making an Activity Diagram for the HLD | Finish the Activity Diagram, and start the Data Flow Diagram.
Faisal | No | Worked with Abhay in making Diagrams for HLD | Work on BRD and HLD
Kevin | No | No work. Spent the day studying for midterms | I will work on the project plan after the team talks about estimated time for each task
2022-10-04 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | work on BRD and HLD | Work on use cases functional requiremnets for BRD
David | Yes | I changed small parts of the project plan and was unable to get together to work on time estimates so I still need to work on getting time estimates. | I will try to finish the roadmap of the project plan and if I have time work more on the project plan time estimates.
Bryant | No | I worked on the BRD NFRQ and FRQ. | I will work on the BRD and adding work items to the project backlog.
Abhay
Faisal | No | Worked on BRD and HLD | plan new sprint
Kevin
2022-10-05 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra | No | Work on use cases functional requiremnets for BRD | Work on project plan
David | No | I completed the Roadmap of the project plan. | I will work on the detailed plan of the project plan
Bryant | No | I worked on BRD and Project Backlog. | I will continue working on Project Backlog.
Abhay |  |  | Finishing the High Level Design
Faisal
Kevin

## Daily Stand-ups 3-5
Daily Stand-ups Sprint 3
2022-10-06 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Kevin
2022-10-07 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Kevin
2022-10-08 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Kevin
2022-10-09 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Kevin
2022-10-10 | Are you blocked? | What did you do yesterday? | What are you going to do today
Sierra
David
Bryant
Abhay
Faisal
Kevin